## Slide 1
Digitizing Savings Groups - Concept Note

## Slide 2: Context
In 2020 - 2021, FSD Africa conducted research to assess the feasibility of digitizing government to person (G2P) social protection payments and humanitarian cash transfers in Nigeria.
The methodology for this research included a combination of desk research, key informant interviews and focus group discussions with cash transfer recipients.
The results of this research were published in a report and accompanying roadmap, which made specific recommendations for advancing the digitization of cash transfers in Nigeria.
One of these recommendations included digitizing savings groups.

## Slide 3: Cash is Still the Preferred Disbursement Modality amongst Recipients
Recipients of unrestricted cash transfer programs typically prefer receiving physical cash rather than digital disbursements into an account. Focus group sessions with recipients uncovered a variety of reasons for their preference of cash, including:
For cash programming to have a positive impact on increasing access to financial services for program participants, more value proposition and familiarity must be derived from the digital funds than currently exists, as currently cash is simply the more fitting option.
Unfamiliarity with digital delivery mechanisms
Low levels of trust in formal financial institutions
Limited number of use cases (e.g. school fee payment, savings group wallet) beyond cashing out an funds received digitally

## Slide 4: Why is Digitizing Savings Groups Relevant for Cash Transfer Recipients?
Many cash program participants are members of savings groups and actively save and access informal credit through this channel. Digitizing savings groups can help deliver additional value to savings groups members, while also introducing them to digital tools and services.
Evidence shows that linking savings groups to formal financial institutions brings a variety of benefits:
Improved safety of funds for larger groups
Increase in financial performance, particularly for groups that are able to access larger credit facilities to on-lend within groups
Having access to formal savings accounts allow groups to save for longer than one cycle (groups typically need to start from zero after each cycle).

## Slide 5: What is this concept note proposing?
This project will launch a digital savings group service with cash transfer recipients in collaboration with Action Against Hunger and EFINA.
By tapping the network of savings groups Action Against Hunger facilitates, this concept note seeks to aggregate demand for digital savings services, which will reduce market entry barriers the digital savings group platform that will eventually be engaged. This project will also test digitizing savings groups on a wider scale, observing where key benefits to the groups develop and attempting to determine whether digitizing other aspects of the savings group members’ financial lives can increase their willingness to receive cash programming digitally.
In the context of this project, digitizing savings groups means 1) digitizing the group bookkeeping/ledger 2) testing the potential of a digital wallet solution for the group, and 3) seeking ways to link savings groups to formal financial services through digital channels.

## Slide 6: Key Project Questions
1. What are the impacts of digitization on group dynamics (disputes, conflicts) and group assets (savings, credit)?
2. Can digitizing savings groups help expand cash program recipient access to formal financial services through linkages to financial service providers?
3. Can digitizing savings groups help pave the way for digitizing cash transfer payments by creating more familiarity, trust and digital literacy amongst cash program recipients?
4. Can digitizing savings groups build additional use cases around a transactional wallet/account that encourages less dependence on cashing out?
5. What are the impacts of digitization on financial service provider interest in serving savings groups and their members?
6. Can digital savings group platforms (e.g. digital ledgers, wallets) build commercially viable models in Nigeria?

## Slide 7: Phase 1: Data Alignment
In this phase the Action Against Hunger and will ensure data on savings groups they manage is well aligned with project objectives. No personally identifiable information will be exchanged or used during this process. This will:
The database can also serve as a baseline for some important data points for monitoring and evaluation of the project.
Provide the digital savings group platform with sufficient information on the key functionality requirements & habits, norms and preferences of savings group members to provide stronger proposals to the consortium
Help quantify the amount of savings groups, members, savings, and credit that is represented with the consortium. This will be important to determine where to pilot. It will also be helpful in discussions with financial institutions.

## Slide 8: Phase 2: Procurement of a digital savings group platform
This procurement seeks to find a digital savings group platform that is the best fit for Action Against Hunger and the savings groups they work with. EFINA will support Action Against Hunger in the development of an RFP agreeing on a specific statement of requirements that will enable a smooth proposal process for potential digital savings group platforms. Some examples of key functionalities the RFP will seek to vet are:
Onboarding : What are the details of the onboarding and registration process is for the app
Offline Capabilities: Does the product allow for data collection when there is no network?
Feedback: What are the channels for group members to troubleshoot and provide feedback?
Device requirements: What hardware does a group need to interact with the product?
Notes: Full list
Data Protection: Ensuring savings groups have control over how their data will be used is essential. As part of the RFP process for the digital savings group platform, it will be key to assess how data is stored, protected, and where the consent of savings group members is required and captured. Ensuring providers can align with the Nigerian Data Protection legislation passed in 2019 will be part of the scoring criteria.
Customer Onboarding: What does the onboarding process look like and are there elements of KYC conducted (see data privacy as well here). Can onboarding be done digitally (e-KYC) or face to face?
Off-line capabilities: Can data be collected by groups in areas without network coverage?
Data burden: How much bandwidth does the app require, and what will be the amount of data required to use the app on average?
Feedback/Grievance Systems: How does the platform provider support group members when they run into issues with the service?
Digital literacy and onboarding: How do the platform provider build digital literacy amongst group members. How does the provide help educate members to avoid any potential fraud?
Messaging and Communication: How does the platform improve the ability of the group to communicate, air grievances, and provide feedback with key stakeholders?

## Slide 9: Phase 3: Primary Data Collection (Baseline) and Pilot Location Selection
Action Against Hunger and EFINA, in coordination with the selected digital savings group platform provider, will build questionnaires that can be deployed at a sample of group meetings. Action Against Hunger staff can facilitate the data collection activities. Using the findings from this data collection exercise, locations and specific groups can be selected for the pilot. A key piece of information will likely be smartphone penetration, and mobile phone penetration amongst group members. Typically at least one smartphone per group is necessary to interact with the digital savings group platform. At the end of this phase pilot locations and groups will be selected.
Some examples of key characteristics a savings group that is potentially ready for digitization can be found below:
Groups with charismatic leadership tend to be more successful
Groups should have some younger members that will likely be more willing to use the smartphone
Groups should have one or two members with reasonable digital literacy
Groups should be in areas with mobile network connectivity
Group members should have access to ID, if possible, as that will be a requirement for formal financial account linkages
Notes: Data Protection: Ensuring savings groups have control over how their data will be used is essential. As part of the RFP process for the digital savings group platform, it will be key to assess how data is stored, protected, and where the consent of savings group members is required and captured. Ensuring providers can align with the Nigerian Data Protection legislation passed in 2019 will be part of the scoring criteria.
Customer Onboarding: What does the onboarding process look like and are there elements of KYC conducted (see data privacy as well here). Can onboarding be done digitally (e-KYC) or face to face?
Off-line capabilities: Can data be collected by groups in areas without network coverage?
Data burden: How much bandwidth does the app require, and what will be the amount of data required to use the app on average?
Feedback/Grievance Systems: How does the platform provider support group members when they run into issues with the service?
Digital literacy and onboarding: How do the platform provider build digital literacy amongst group members. How does the provide help educate members to avoid any potential fraud?
Messaging and Communication: How does the platform improve the ability of the group to communicate, air grievances, and provide feedback with key stakeholders?

## Slide 10: Phase 4: Financial Service Provider Engagement
These discussions are meant to gauge the interest of financial service providers in delivering services to savings groups, and to establish early interest in partnerships between the digital savings group platform and FSPs.
These discussions do not necessarily need to end in partnership agreements but should help establish relationships with financial institutions that could play a role long term in financial service delivery to digitized savings groups.
As part of these discussions, Action Against Hunger will share current information on the managed savings groups. It will be important to understand what type of information or data would be interesting for financial institutions and help them to make more informed decisions about partnerships in the future. Any data sharing that occurs with potential financial partners will need to have consent factored in.

## Slide 11: Phase 5: Pilot Planning
Field Force Development - The training of trainers (ToT) will need to be conducted by the platform provider and whoever will be doing customer acquisition and onboarding for the pilot (with Action Against Hunger staff and them in onboarding and customer support).
Group Acquisition Activities - Group onboarding and acquisition will need to involve educational elements of not only how to navigate and use the product, but other elements of digital literacy such as how to reduce data bundle usage and costs on a smartphone. The onboarding sessions will also need to educate members on potential fraud and provide solutions for ways to mitigate the risk of fraud. All groups will need to have access to a minimum of 3G connectivity.
Smartphone/Tablet procurement - Action Against Hunger has elected to completely subsidize the smartphone (via budget from this concept note), and partially subsidize the data bundle, with gradual reduction of the data bundle subsidy over the pilot period.
Digital Financial Literacy - The deployment of digital financial literacy will be important during the group onboarding process. There are a variety of open source resources including GSMA’s MISTT and USAID’s Hey Sister Show Me the Mobile Money.

## Slide 12: Phase 6: Pilot Implementation
1. Onboarding and Troubleshooting
Action Against Hunger and digital savings platform partner will roll out the pilot by training and onboarding groups. Throughout the pilot, groups will be monitored closely, and face to face check-ins will occur on a monthly basis in line with group meetings
2. Financial Service Provider Partnerships
After the third month of the pilot, Action Against Hunger and EFINA will work with the digital savings platform to analyze savings and credit patterns of the groups. This data will be used to continue the engagements with the prospective financial service provider partners.
3. Field Force Ownership Transfer
During the first six months of the pilot, the Action Against Hunger and EFINA will work with the digital savings platform partner to consider ways to transfer savings group facing activities over to a field force that is either owned directly by the digital savings platform partner or a partner financial institution.
4. Revenue Model Assessment
The digital savings platform partner will provide data on current and projected revenue potential for their operations in Nigeria. This will be an important part of the pilot’s ongoing reporting, to help analyze the likelihood of sustainability post project.

## Slide 13: Phase 7: Endline Data Collection and Report Development
The final phase of this pilot process will be to conduct endline data collection to get direct feedback from the groups in addition to using data from the digital savings group platform dashboard.
Using this data, Action Against Hunger and EFINA will provide a final analysis on the key performance indicators and build a report providing details on the results in addition to key recommendations for potential pathways to scaling the solution in Nigeria. The report will highlight key challenges and questions that have been left unanswered, in addition to delivering advice on key points of leverage these digital savings products can be used to bring more savings group members onto digital financial service solutions.
The analysis will also examine the comfort levels of group members in using digital services and determine whether there has been an increase in usage of digital financial services on an individual basis as a result of group digitization.

## Slide 14: Budget & Workplan
Link to Budget
Link to Workplan

## Slide 15
Thank You!